## Sheet1
Team Meetings
Date | Start-End Time | Mins | Minutes of the Meeting
2022-03-21 | 11:00AM - 12:00PM | 60 | Brainstormed ideas for project 3.
2022-03-22 | 9:00AM - 9:45AM | 45 | Divided tasks, brainstormed language and platform.
2022-04-01 | 9:00AM - 10:00AM | 60 | Discussed progress. Helped debug errors.
2022-04-02 | 10:00PM - 10:45PM | 60 | Discussed any changes needed.
2022-04-04 | 12:00PM - 1:00PM | 60 | Tested the calculator and made final changes.
Total Mins
285
We estimated that the design stage for the project 3 would take 4 hours, implementing for 7 hours,
debugging for 3 hours, and commenting/documentation for 2 hours.

## Sheet2
Time Log (Actual)
Date | Huzaifa Zahid | Mir Shazil Faisal | Zhenzhou Wang | Junyi Zhao
2022-03-27 | 1 | - | 0.5
2022-03-28 | - | - | 1
2022-03-29 | - | - | -
2022-03-30 | - | - | 1.5
2022-03-31 | 1 | - | -
2022-04-01 | 2 | 0.5 | 1.5
2022-04-02 | - | 1.5 | 1.5
2022-04-03 | 1 | 3 | 1
Total Hours: | 5 | 5 | 7